## Sheet1
ElderSens projects summary
Action Item | Description | Lead | Timeline | Status
DiaperSens baseline HW | Sensor (SSK) + Router (Pi) + Alert device (display, SMS…) | 张华全
DiaperSens baseline SW | cloud based software, IOS and Android App | 黄旭
DiaperSens Amazon listing documents, accounts | Accounts, Certificate application, reference to Opro9 | 田敏 | 已完成 | Applied Amazon account, Apply UPC (SN#)
DiaperSens Amzon listing product preparation | video | 郑永强 | 已完成 | 目前视频已经完成 如有新的视频任务 可以再进行拍摄
DiaperSens HongKong deployment App | IOS and Android App | 叶家俊 | 2018-03-19 | App已完成大部分功能，仍需要完成推送，图表，警报三个功能。
Disposable Engine |  | 郑永强 | 三月十六日 | 第一版样品已经送出，改进后本周内可以完成3d打印的设计
ElderSens router | 原理图和PCB | 谢高翔 | 2018-03-16 | 原理图设计
DiaperSens Gen2 Sensor OEM ChangHong |  | 张华全, 郑永强
DiaperSens products readiness | Sensor product for Amazon listing, and system for demo | 刘松